## Projects
project_id | project_name | descriptions | project_manager | client_name | created_date | start_date | due_date | status | priority | completion_percentage
PRJ-001 | GeoPulse 1.0 | Satellite-based land change analysis platform that combines cutting edge remote sensing technology with modern web API's | Ravi Kiran | Nageshwar Rao (MRO) |  |  |  | IN_PROGRESS | HIGH | 0
PRJ-002 | GeoPulse 2.0 | The project is the second version of Geopulse application. Primary requirements are 1. clear images 2. Agentic way of performing the decisions. | Ravi Kiran | Ashwin Pingali | 2025-10-23 | 2025-10-24 | 2025-10-31 | NOT_STARTED | HIGH | 0
PRJ-003 | INR | INR home foods - practice for digital marketing(retail business) |  | Charan |  |  |  | NOT_STARTED |  | 0
PRJ-004 | First Cry | first cry-practice for digital marketing(franchise business) |  | Jithendra |  |  |  | NOT_STARTED |  | 0
PRJ-005 | Sridevi Agency | sridevi agency-practice for digital marketing(wholesale business) |  | RK |  |  |  | NOT_STARTED |  | 0
PRJ-006 | Learnings |  |  | self
PRJ-007 | content creation and posting | create a content based on the topics planned and post in various multiplatforms | [5 empty] | NOT_STARTED |  | 0
PRJ-008 | Careercatalyst | A training program for students |  | Data legos |  |  |  | NOT_STARTED |  | 0
PRJ-009 | Marketing | marketing plan and strategy for data legos and career catalyst |  | Data legos
PRJ-010 | Operation | internal operation for data legos |  | Data legos
PRJ-011 | Finacial | financial requirments and taska dor DL |  | Data legos |  |  |  | NOT_STARTED |  | 0
PRJ-012 | Monthly Tasks | monthly re-occuring tasks for each employee and DL | Tech Team | Data legos |  |  |  | NOT_STARTED |  | 0
PRJ-013 | Daily Tasks | daily re-occuring tasks for each employee and DL | OPS Team | Data legos |  |  |  | NOT_STARTED |  | 0
PRJ-014 | Automations | create automations for both DL and small business | OPS Team | Data legos |  |  |  | NOT_STARTED |  | 0
PRJ-015 | Vlog videos | Road trip videos converting into youtube vlogs in multilingual videos | Naveen | Ravi Kiran | 2025-10-23 | 2025-10-27 | 2025-10-31 | NOT_STARTED | HIGH | 0
PRJ-016 | Project Tracking Automation | This automation monitors the subtasks and update/notify the status and completion of every task when they are changed | Ravi Kiran | Data legos | 2025-09-08 | 2025-09-08 | 2025-10-31 | NOT_STARTED | HIGH | 0
PRJ-017 | eBhoomiRecords |  | Ravi Kiran | Nageshwar Rao (MRO) |  |  |  | NOT_STARTED | HIGH | 0
PRJ-018 | Roads&Ridges-Raki Diaries- Phase-1 | 3RD-Raki's road trip in usa videos publishing to the youtube. As is video. | Naveen | Ravi Kiran | 2025-11-01 | 2025-11-01 | 2025-12-31 | NOT_STARTED | HIGH | 0
PRJ-019 | lead generation | search for projects and freelancing jobs around the world | Gokul | Data legos | 2025-11-03 | 2025-11-04 |  | NOT_STARTED | HIGH | 0
PRJ-020 | RCM+UiPath: Patient Eligibility Verification | This project helps to verify the Patient Eligibility for insurance and simplify the long process | Ravi Kiran | Ravi Kiran | 2025-11-05 | 2025-11-08 | 2025-11-14 | COMPLETED | HIGH | 100
PRJ-021 | DL website | This is internel project which is our webpage |  | Data Legos | 2025-11-11
PRJ-022 | RCM+UiPath: Denial Management | The Denial Management Automation system is designed to streamline the process of handling insurance claim denials in healthcare revenue cycle management. | Ravi Kiran | Ravi Kiran | 2025-11-11 | 2025-11-11 | 2025-11-12 | NOT_STARTED | HIGH | 0
PRJ-023 | UiPath Automation on Email to Google Sheet | This automation helps to get noticed who sent the email and what is the subject of the email in your sheet | Ravi Kiran | Ravi Kiran | 2025-11-11 | 2025-11-13 | 2025-11-14 | NOT_STARTED | HIGH | 0
PRJ-024 | POCs | Taking the new technologies or frameworks and implementing | Ravi Kiran | Ravi Kiran | 2025-11-21 | 2025-11-21 |  | IN_PROGRESS | HIGH

## Usecases
usecase_id | project_id | usecase_name | descriptions | owner | start_date | due_date | status | completion_percentage
UC-001 | PRJ-002 | Enabling the Users to upload different forms of input. | Location Input & Validation Accepts geographic areas using: GeoJSON polygons Lat-long + radius Street addresses (auto-geocoded) Supports areas from 250 m² up to 100 km². Validates coverage within Planet’s imaging zones. |  | 2025-10-23 | 2025-10-24 | NOT_STARTED
UC-002 | PRJ-003 | generate a feed back form for INR curry point | modify the general feed back form to use for INR home foods. |  |  |  | NOT_STARTED | 0
UC-003 | PRJ-003 | Prepare the deliverables to handover to INR curry point | modify the general delverables form to use for INR home foods. |  |  |  | NOT_STARTED | 0
UC-004 | PRJ-004 | preapre a detailed plan to impliment in First cry | preapre a detailed plan to impliment in First cry .discuss the tasks and assign to each team member |  |  |  | NOT_STARTED | 0
UC-005 | PRJ-005 | preapre a detailed plan to impliment for Sridevi Agency | preapre a detailed plan to impliment in sridevi agency .discuss the tasks and assign to each team member
UC-006 | PRJ-008 | prepare the video list for students training | list the topics we discussed so far to prepare videos for students for their training
UC-007 | PRJ-002 | Adding LLM to the application to generate report summary to the surveyor.. | the llm need to be added to generate reports summary.. |  | 2025-10-24 | 2025-10-25
UC-009 | PRJ-011 | enter the pending expenses from statments for data legos | check the sheet, see from which months entry is missing and collect pending statments from ravi sir and fill the sheet
UC-010 | PRJ-001 | Testing Geopulse | Testing Geopulse to ensure all functionalities work |  | 2025-09-15 | 2025-10-31 | IN_PROGRESS | 0
UC-011 | PRJ-002 | enabling the users to see the changes in the visually through the images | we are going to retrieve the images as well for the two dates to see the changes visually.
UC-012 | PRJ-012 | generate the payslips for employess | generate monthly payslips for team |  | 2025-10-31 | 2025-10-31
UC-013 | PRJ-012 | preparing the necesscities to track teams monthly progress | prepare a routine to track teams progress and updates |  | 2025-10-30 | 2025-10-31
UC-014 | PRJ-002 | boosting the performance and computing efficiency by caching storage.. | Local caching to reduce downloads. Progressive loading for large areas. Metadata storage for quick historical queries.
UC-015 | PRJ-013 | prearing for daily standups for team | conduct daily standup for team mates check the progress of their work and to keep track of their work |  | 2025-10-27 | 2025-10-27
UC-016 | PRJ-013 | entering time log and work entry | fill excel and also clokify regularly make sure team does the same |  | 2025-10-27 | 2025-10-31
UC-017 | PRJ-013 | preparing the prompt for making ve03 videos | practice prompt for veo3 video generation |  | 2025-10-27 | 2025-10-27
UC-018 | PRJ-014 | creating 2 automatioms for DL | create any two automations daily it can be a simple one too |  | 2025-10-27 | 2025-10-31
UC-019 | PRJ-013 | doing any admin works | check and complete the admin work for DL |  | 2025-07-01
UC-020 | PRJ-007 | planning for daily content posting | need to post daily content across multiple platforms - prepare a template based on the requirments |  | 2025-10-27 | 2025-10-28
UC-021 | PRJ-015 | preparing a clear story plan how to make a perfect vlog style videos | first video making on the grandjunction all the videos |  | 2025-10-27 | 2025-10-31 | IN_PROGRESS
UC-022 | PRJ-016 | Automation Creation for project Tracking | this automation tracks the projects status and completion progress |  | 2025-09-08 | 2025-10-31 | NOT_STARTED | 0
UC-023 | PRJ-001 | Organization Setup | Removed delete button from Organization Setup admin page |  | 2025-10-23 |  | COMPLETED
UC-024 | PRJ-001 | Delete Button Reports Page | Removed debug information section from Reports page |  | 2025-10-24 |  | COMPLETED
UC-025 | PRJ-001 | Debug Cleanup Contact Phone Display | Fixed contact phone field fetching in user profile |  | 2025-10-25 |  | COMPLETED
UC-026 | PRJ-001 | Surveyor Dashboard Issue | Diagnosed authentication issues with surveyor dashboard |  | 2025-10-26 |  | COMPLETED
UC-027 | PRJ-002 | looking for imagery retrieval to enable user to understand changes visually | analysing how cn we get the images.. |  | 2025-10-27
UC-028 | PRJ-017 | Testing eBhoomiRecords webapplication | this ebhoomirecords webportal has admin login and userlogin | Sathwik | 2025-10-28 | 2025-10-29 | IN_PROGRESS
UC-029 |  | 3RD-Self Explain videos about the journey, preparation and mindset during the journey | About the overall journey video which are not directly related to a place as such. Could be a special thing in that place, but topic is global. | Naveen | 2025-11-01 | 2025-11-04 | IN_PROGRESS
UC-030 | PRJ-018 | Grand Junction - Local | GrandJunction local attactions like Monument, downtown, events, accomodation etc. | Naveen | 2025-11-01 | 2025-11-04 | NOT_STARTED | 0
UC-031 |  | Grand Juntion - Grand Mesa | Trip to GrandMesa | Naveen
UC-032 |  | Grand Juntion - Moab | Moab Arches national park trip .
UC-033 |  | Grand Juntion - Canyon Lands | canyaon lands drive
UC-034 |  | Grand Junction - Vine yards | Vist to vine yards in grandjuction
UC-035 |  | Montrose - Local | montrose to Grandjuction . withink montrose village tour, farmers market, austrilan show, downltown,
UC-036 |  | Montrose - black canyon | Black canyon trip with gunnison river
UC-037 |  | Montrose - crusted Brutt | Crsuted brutt trip may be 3 to 4 videos of content.
UC-038 |  | Montrose - ouray | 2. million dollor highway 3. ouray downtown
UC-039 |  | Montrose- hotsrpings | 1. hotstprings experiance
UC-040 |  | Montrose-telluride | telluride downtown and gandola trip 3 to 4 videos
UC-041 |  | Durengo- local and stay | local as well as Durango to Back to denver
UC-042 |  | Denver to Albaquerue | Taos, native indians staying.
UC-043 |  | Albaquerque - Local and surroundings | gandola trip, motorcyle trip to santafe, native indians caves and civilization
UC-044 |  | Dallas local experiences
UC-045 |  | Dallas to Austin
UC-046 | PRJ-019 | projects - US | find projects from US market
UC-047 |  | freelancers- US | find freelancing market
UC-048 | PRJ-020 | Checking the insurance eligibility of the patient | With the data of the patients and payers we can see who is eligible for the insurance | Sathwik | 2025-11-08 | 2025-11-12 | COMPLETED | 100
UC-049 | PRJ-022 | Create a UiPath Automation on Denial Management | The system will automatically parse denial codes from Explanation of Benefits (EOB) documents or Electronic Remittance Advice (ERA) files, classify denials by reason, generate summary reports, and enable quick corrective action by billing teams. | Sathwik | 2025-11-11 | 2025-11-12 | NOT_STARTED | 0
UC-050 | PRJ-023 | New Email Log maintainer in sheet | This will scrape the data from the mail to sheet like senders email and subject of the email | Sathwik | 2025-11-13 | 2025-11-14 | NOT_STARTED | 0
UC-051 | PRJ-024 | Business case agentic application flow | Need to work with agent and implementing an agent for a business case | Sathwik | 2025-11-21 |  | NOT_STARTED | 0

## Userstories
userstory_id | usecase_id | project_id | userstory_name | description | acceptance_criteria | owner | start_date | due_date | status | completion_percentage
US-001 | UC-001 | PRJ-002 | adding a feature to upload multiple input formats. | Location Input & Validation Accepts geographic areas using: GeoJSON polygons Lat-long + radius Street addresses (auto-geocoded) Supports areas from 250 m² up to 100 km². Validates coverage within Planet’s imaging zones. |  |  |  |  | NOT_STARTED | 0
US-002 | UC-002 | PRJ-003 | Adding LLM to the application to generate report summary to the surveyor.. | the llm need to be added to generate reports summary..
US-003 | UC-003 | PRJ-003 | enabling the users to see the changes in the visually through the images | we are going to retrieve the images as well for the two dates to see the changes visually.
US-004 | UC-004 | PRJ-004 | boosting the performance and computing efficiency by caching storage.. | Local caching to reduce downloads. Progressive loading for large areas. Metadata storage for quick historical queries.
US-005 |  | PRJ-003 | document preparation for delivarables to INR | document preparation for delivarables to INR |  |  | 2025-10-27
US-006 |  | PRJ-003 | document preparation for feedback to INR | document preparation for feedback to INR |  |  | 2025-10-27
US-007 |  | PRJ-004 | planning for 3 day digital marketing to execute for first cry | planning for 3 day digital marketing to execute for first cry |  |  | 2025-10-27
US-008 |  | PRJ-005 | planning for 3 day digital marketing to execute for sridevi agencies | planning for 3 day digital marketing to execute for sridevi agencies |  |  | 2025-10-27
US-009 | UC-010 | PRJ-001 | Application using experience | In the user perspective we need to get the smooth experenice in every interface and all the functionalities work |  |  | 2025-09-15 |  | COMPLETED | 0
US-010 |  | PRJ-008 | planning for making videos to give to students for learning | prepare a detailed flow and techiques for making videos to students undrestanding |  |  | 2025-10-27
US-011 |  | PRJ-011 | enter the pending expenses from statments for data legos to track expenses. | check the sheet, see from which months entry is missing and collect pending statments from ravi sir and fill the sheet |  |  | 2025-10-27
US-012 |  | PRJ-012 | creating payslips for employees monthly to pay sallary | generate monthly payslips for team |  |  | 2025-10-31
US-013 |  | PRJ-012 | report generation for teams monthly status | generate a monthly team achivements and progress by collecting data from excel and clockify |  |  | 2025-10-31
US-014 |  | PRJ-013 | conducting daily standups for team to track progress and updates | conducting daily standups for team to track progress and updates |  |  | 2025-10-31
US-015 |  | PRJ-013 | enetring the taks and sheets for daily followups and tracking | enetring the taks and sheets for daily followups and tracking |  |  | 2025-10-31
US-016 |  | PRJ-013 | generating AI videos daily using veo3 to improve prompt and perfection | generating AI videos daily using veo3 to improve prompt and perfection |  |  | 2025-10-31
US-017 |  | PRJ-014 | building automations useful for DL and other | identify and building automations useful for DL and other |  |  | 2025-10-27
US-018 |  | PRJ-013 | doing admin works if anything comes up | doing admin works if anything comes up |  |  | 2025-10-31
US-019 |  | PRJ-007 | gathering requirments for creating content to post online | gathering requirments for creating content to post online |  |  | 2025-10-27
US-020 | UC-010 | PRJ-001 | Threshold Accuracy | The user must expect the accurate results to check where they has to go or not |  |  | 2025-10-24 | 2025-10-28 | NOT_STARTED | 0
US-021 | UC-022 | PRJ-016 | Automation on project tracking | Automation testing that notify the changes of tasks and notify the completion and due date tasks |  |  | 2025-09-08 | 2025-10-31 | IN_PROGRESS | 0
US-022 |  | PRJ-002 | Imagery | User can view the changes visually |  |  | 2025-10-27 |  | IN_PROGRESS
US-023 | UC-030 | PRJ-018 | Grand Junction | need to create 4 videos in grandjunction Raki travel intro, home tour, grand junction main monument |  |  | 2025-11-03 |  | IN_PROGRESS
US-024 | UC-048 | PRJ-020 | A insurance departement verification time | As a Insurance Department member i want to reduce my time by checking the data of the patients with the payer (insurance compnay) |  | Sathwik | 2025-11-08 | 2025-11-12 | COMPLETED | 100
US-025 | UC-049 | PRJ-022 | Denial Management | I want to get the detials and reduce my time to check the policy claim will work or soft denial or hard denial |  | Sathwik | 2025-11-11 | 2025-11-12 | IN_PROGRESS
US-027 | UC-050 | PRJ-023 | Email log entry in sheet |  |  | Sathwik | 2025-11-13 | 2025-11-14 | NOT_STARTED

## Tasks
task_id | userstory_id | project_id | task_name | description | owner | start_date | due_date | priority | status | completion_percentage
TK-001 | US-001 | PRJ-002 | adding a feature to upload multiple input formats. |  | Sumanth
TK-002 | US-001 | PRJ-002 | Adding LLM to the application to generate report summary to the surveyor.. |  | Sumanth
TK-003 | US-001 | PRJ-002 | enabling the users to see the changes in the visually through the images | need to do analysis youtube, claude, kiro.... Need to do analysis on retrieving the geographical images from the satillite using different apis and see how can we get the images just need to watch the videos.. | Sumanth
TK-004 | US-001 | PRJ-002 | boosting the performance and computing efficiency by caching storage.. |  | Sumanth
TK-005 |  | PRJ-003 | delivarables document template preparation | preapare the delivarbales document template and 1. collect all the deliverbales and give it to INR
TK-006 |  | PRJ-003 | feed back document template preparation | preparing the feedback document and giving to the INR for what we done and taking feedback from them so it would be template for us to complete another bussiness
TK-007 |  | PRJ-004 | team discussion and modifying 3 day digital marketing template to execute for first cry | team discussion and modifying 3 day digital marketing template to execute for first cry
TK-008 |  | PRJ-004 | team discussion and modifying 3 day digital marketing template to execute for sri devi agencies | team discussion and modifying 3 day digital marketing template to execute for sri devi agencies
TK-009 |  | PRJ-008 | preparing plan and template for making videos to give to students for learning | preparing plan and template for making videos to give to students for learning
TK-010 | US-009 | PRJ-001 | Test Admin Login | Admin has power to create organization, admins, user, subscription, thresholds |  | 2025-09-22 |  | HIGH | COMPLETED
TK-011 | US-009 | PRJ-001 | Test Surveyor Login | User can upload and generate reports of that land with the required indicator and threshold |  | 2025-09-22 |  | HIGH | COMPLETED
TK-012 |  | PRJ-011 | collect pending statments from ravi sir | check the sheet, see from which months entry is missing and collect pending statments from ravi sir and fill the sheet
TK-013 |  | PRJ-012 | run payslips for employees monthly to pay sallary | run payslips for employees monthly to pay sallary
TK-014 |  | PRJ-012 | generate report for teams monthly status | generate report for teams monthly status
TK-015 |  | PRJ-013 | conducting daily standups for team to track progress and updates | conducting daily standups for team to track progress and updates
TK-016 |  | PRJ-013 | enetring the taks and sheets for daily followups and tracking | enetring the taks and sheets for daily followups and tracking
TK-017 |  | PRJ-013 | generating AI videos daily using veo3 to improve prompt and perfection fro each and every google account | generating AI videos daily using veo3 to improve prompt and perfection fro each and every google account
TK-018 |  | PRJ-014 | find anf builld 2 automations daily useful for DL and other | daily task creating any workflow automations that should be either simple or complex daily 2 automations should complete
TK-019 |  | PRJ-013 | doing admin works if anything comes up | doing admin works if anything comes up
TK-020 |  | PRJ-007 | regular content creation and posting | regular content creation and posting
TK-021 |  | PRJ-014 | daily task 2 automations should complete. | do any two automations |  | 2025-10-21 |  | HIGH | IN_PROGRESS | 75%
TK-022 |  | PRJ-001 | Geopulse-1.0 | Updating to reach the final requirements. |  | 2025-10-27 |  | HIGH | IN_PROGRESS
TK-023
TK-024
TK-025
TK-026 | US-020 | PRJ-001 | Threshold Accuracy Testing | Based on the thresholds the results will be different so need to check the different type of approches and get the highest |  | 2025-10-23 | 2025-10-28 | HIGH | IN_PROGRESS
TK-027 | US-021 | PRJ-016 | creating sheet | creating sheet for the project hirarchy |  | 2025-09-08 | 2025-09-30 | HIGH | COMPLETED
TK-028 | US-021 | PRJ-016 | creating automation on project tracking | the automation has to be track the and update the changes |  | 2025-09-15 | 2025-10-31 | HIGH | IN_PROGRESS
TK-029 |  | PRJ-002 | imagery | Doing analysis on geopulse to retreive the images for both baseline and target dates to enable the user to understand visually |  | 2025-10-27 |  | HIGH | IN_PROGRESS
TK-030 |  | PRJ-001 | Deploy the Geopulse 1.0 in the Production server. | Deploy the Geopulse 1.0 with the Docker and ansible in the production server. | Vishnu | 2025-03-11 | 2025-08-11 | HIGH | IN_PROGRESS
TK-031 |  | PRJ-021 | Updating chatbot | this is the task that i was assigned to... to update the dl website chatbot | Sumanth | 2025-11-10 | 2025-11-11 | HIGH | NOT_STARTED
TK-032 |  | PRJ-021 | Updating DL website as per the new requirements. | updating the cci-chat page for proper responsive, and adding chat bot fro all pages and new adress too. | Vishnu | 2025-11-10 | 2025-11-10 | HIGH | COMPLETED
TK-033 | US-024 | PRJ-020 | UiPath Automation for Patient Eligibility Verification |  | Sathwik | 2025-11-08 | 2025-11-11 | HIGH | COMPLETED | 100

## Subtasks
d | task_id | project_id | subtask_name | description | assigned to | start_date | due_date | status | completion_percentage | comments | last_updated | updated_by
STK-001 |  | PRJ-003 | delivarables document template preparation | preapare the delivarbales document template and 1. collect all the deliverbales and give it to INR | Gokul | 2025-10-23 | 2025-10-27 | COMPLETED | 100 |  | 2025-12-11 09:55
STK-002 |  | PRJ-003 | feed back form template preparation | preapare the feedback form document template and 1. validate with team and collect feed abck from INR | Gokul | 2025-10-23 | 2025-10-27 | COMPLETED | 100 |  | 2025-12-11 09:55
STK-003 |  | PRJ-004 | modifying 3 day digital marketing template | team discussion and modifying 3 day digital marketing template to execute for first cry take only whats necesary and assign tasks to collect the necessary requirments and divide among team | Gokul | 2025-10-17 | 2025-10-24 | COMPLETED | 100 | discussed and finazlised the template and arranged the folders in google drive | 15/11/25 19:14
STK-004 |  | PRJ-004 | autoposting workflow for firstcry | complete the workflow for autoposting , validate ,demo and deliver it to client | Gokul | 2025-10-23 | 2025-10-28 | COMPLETED | 100 | need to get validation mail from meta | 2025-12-11 09:56
STK-005 |  | PRJ-008 | learning video preparation | validate the topics written till now on one note and check whats needed prepare a template and assaign the video making to ravi sir. | Gokul | 2025-10-22 | 2025-10-27 | IN_PROGRESS | 75 | sent to team sumanth added few topics and most of the topics a re covered. Oct 28: keep all topics in one sheet. gokul and ravi discuss later to prioratize.
STK-006 |  | PRJ-011 | expense filling | check the sheet, see from which months entry is missing and collect pending statments from ravi sir and fill the sheet | Gokul | 2025-10-22 | 2025-11-03 | NOT_STARTED |  | oct 28: will review. | 15/11/25 19:15
STK-007 |  | PRJ-012 | daily standups and meet for team | conduct daily standups for team to track progress and updates. | Gokul | 2025-10-27 |  | IN_PROGRESS |  |  | 2025-12-11 09:56
STK-008 |  | PRJ-012 | tasks and clockify filling | enetring the taks and sheets for daily followups and tracking, filling the clockify regularly | Gokul | 2025-10-27 |  | IN_PROGRESS
STK-009 |  | PRJ-013 | veo3 video creation (Subcription utilizaion) | we have multiple subscriptions for veo3. this limit will expire at the end of the date. we should maintain a list to utilize the subsceription very well by scheduleing and maintaiing the backlog. check the tasks and if needed any videos genrate it and if not needed use some theme and craft the propt and check results | Gokul | 2025-10-27 |  | IN_PROGRESS |  | veo 3 video making in progress | 2025-12-11 09:57
STK-010 |  | PRJ-007 | template preparation for content posting | prepare a template to make the daily content posting fast and efficient | Gokul | 2025-10-24 | 2025-10-28 | IN_PROGRESS |  |  | 2025-12-11 09:57
STK-011 |  | PRJ-001 | modifying organization page | Removed delete button from Organization Setup admin page | Vishnu | 2025-10-24 | 2025-10-24 | COMPLETED | 100
STK-012 |  | PRJ-001 | modifying reports page | Removed debug information section from Reports page | Vishnu | 2025-10-24 | 2025-10-24 | COMPLETED | 100
STK-013 |  | PRJ-001 | modifying profile section | Fixed contact phone field fetching in user profile | Vishnu | 2025-10-24 | 2025-10-24 | COMPLETED | 100
STK-014 |  | PRJ-001 | modifying surveyor dashboard page. | Diagnosed authentication issues with surveyor dashboard | Vishnu | 2025-10-24 | 2025-10-24 | COMPLETED | 100
STK-015 |  | PRJ-003 | clear delivarables document template preparation | preapare the delivarbales document template and 1. collect all the deliverbales and give it to INR | Naveen | 2025-10-23 | 2025-10-27 | IN_PROGRESS | 75
STK-016 |  | PRJ-008 | learning video preparation | Verifying all the topics written till now on one note and check whats needed prepare a template and keep it in onenote [DL_techteam, common, ccstudentapproach, training topics for cc raki] | Naveen | 2025-10-22 | 2025-10-27 | IN_PROGRESS | 75
STK-017 |  | PRJ-013 | veo3 video creation | check the tasks and if needed any videos generate it and if not needed use some local images videos and do it both AI and Manual | Naveen | 2025-10-27 |  | NOT_STARTED
STK-018 |  | PRJ-012 | daily tasks and enter into the clockify filling | note down the daily tasks must enter into the clockify and sheets and followup and tracking and fillup regularly. | Naveen | 2025-10-27 |  | IN_PROGRESS
STK-019 |  | PRJ-004 | modifying 3 day digital marketing template | team discussion on 3 day digital marketing template and updated new ideas | Naveen | 2025-10-17 | 2025-10-24 | COMPLETED | 100
STK-020 |  | PRJ-004 | modifying 3 day digital marketing template | team discussion on 3 day digital marketing template and updated new ideas | Sathwik | 2025-10-17 | 2025-10-24 | COMPLETED | 100
STK-021 | TK-010 | PRJ-001 | Testing admin access and remaining functionalities | Testing every section in the admin login to ensure all functionalities work clear and attached the report link at the comments | Sathwik | 2025-09-22 | 2025-09-29 | COMPLETED | 100 | Testing Report
STK-022 | TK-011 | PRJ-001 | Testing surveyor access and remaining functionalities | Testing every section in the surveyor login to ensure all functionalities work clear and attached the report link at the comments | Sathwik | 2025-09-22 | 2025-09-29 | COMPLETED | 100 | Testing Report
STK-023 | TK-026 | PRJ-001 | Testing bi threshold | testing the bi threshold with different formulas to make sure get the best accuracy | Sathwik | 2025-10-24 | 2025-10-28 | COMPLETED | 100
STK-024 | TK-026 | PRJ-001 | Testing vi threshold | testing the vi threshold with different formulas to make sure get the best accuracy | Sathwik | 2025-10-25 | 2025-10-28 | COMPLETED | 100
STK-025 | TK-026 | PRJ-001 | Testing mixed area of construction and vegitation | testing the both bi and vi threshold with different formulas to make sure get the best accuracy that gets the both construction and vegitation change in changed pixels | Sathwik | 2025-10-27 | 2025-10-28 | IN_PROGRESS | 50
STK-026 | TK-027 | PRJ-016 | creating sheet for the project tracking | create the spreadsheet with the orgainsed tabs and columns that helps to identify and can automate with easy detection of the columns under their specific tabs | Sathwik | 2025-09-08 | 2025-09-15 | COMPLETED | 100 | Project Tracking Automation
STK-027 | TK-028 | PRJ-016 | Creating automation on the project tracker | create the automation on project tracking that identify the updations in subtasks and remaining on status and completion percentage | Sathwik | 2025-09-15 | 2025-10-31 | IN_PROGRESS | 75 | https://workflow.data-legos.com/workflow/85SRf8oGE6E6cARW Needs to add the Discord bot
STK-028 | TK-028 | PRJ-016 | Create automation on due date and deadline notifier | this automation checks the due date and deadline and notifiy according to the date | Sathwik | 2025-09-22 | 2025-10-31 | IN_PROGRESS | 75 | https://workflow.data-legos.com/workflow/85SRf8oGE6E6cARW Needs to add the Discord bot
STK-029 |  | PRJ-001 | Analysing Imagery.. | analyzing the possibilities using the cursor.. | Sumanth | 2025-10-27 | 2025-06-11 | COMPLETED | 100 | analysis completed and pushed the analysis files to the git in datalegos geopulse analysis branch | 15/11/25 19:05
STK-030 |  | PRJ-001 | Debugging Hardcoding Values |  | Vishnu | 2025-10-27 | 2025-10-27 | COMPLETED | 100 |  | 2025-12-11 00:36
STK-031 | TK-003 | PRJ-002 | "geopulse" Doing analysis on imagery requirement | The feature enables the users to get the the visually understandable changes from the two dates given for geopulse 2.0 the detailed analysis synopsis : ----> finding the api which is best for our usecase to get more clear image as well as cost effective.. ----> checking possibility to whether can we use the google earth/any other api by replacing sentinel hub to get the band values.. | Sumanth | 2025-10-28 | 2025-10-28 | COMPLETED | 100 | the analysis on the different apis are done and used them and looked their webpages in order to aware on those apis how to use them for our purose. | 2025-12-11 00:36
STK-032 | TK-003 | PRJ-002 | "geopulse" Developing pocs on imagery requirement using different APIs | Developing the pocs for geopulse 2.0 to get images.. tasks: ----> Implimenting the demo codes for the api to retrieve images.. pushed the code to git "https://github.com/datalegos/GeoPulse/tree/analysis/image_retrieval_analysis" | Sumanth | 2025-10-28 | 2025-10-29 | COMPLETED | 100 | the POC and demo video and md documentation analysis are developed and pushed to git. | 15/11/25 19:06
STK-033 |  | PRJ-001 | Fixing the bugs and errors. | Fixing the bugs and errors in the GP-1.0 | Vishnu | 2025-10-28 | 2025-10-28 | COMPLETED | 100 |  | 2025-12-11 00:36
STK-034 |  | PRJ-001 |  | Rearranging the shared_folder structure and testing the application | Vishnu | 2025-10-29 | 2025-10-29 | COMPLETED | 100
STK-035 |  | PRJ-001 | Moving application to Deployment | Moved applicatoin sucessfully to the production server. | Vishnu | 2025-10-30 | 2025-10-29 | COMPLETED | 100
STK-036 |  | PRJ-004 | Document prepartion-first cry | modify the delivarable document to present to first cry explaining the usage and scope of autoposting workflow | Gokul | 2025-10-31 | 2025-11-02 | COMPLETED | 100 |  | 2025-11-11 13:52
STK-037 |  | PRJ-004 | meeting setup- first cry | setting meeting at the convinince time and delivering the handover documents | Gokul | 2025-10-31 | 2025-11-02 | COMPLETED | 100 | meeting set for monday | 2025-11-11 13:52
STK-038 |  | PRJ-005 | followup-sridevi agencies | follow up with RK anna about GBS status and check for any update or modifications | Gokul | 2025-11-01 | 2025-11-02 | COMPLETED | 100 | mobile num not woking- check and update the num | 2025-11-11 13:52
STK-039 |  | PRJ-005 | ad creation-sridevi agencies | Generate AI ads for sridevi agencies ..shoot the store video ...mix with song and create a complete 1 min ad video | Gokul | 2025-11-01 | 2025-11-03 | COMPLETED | 100 |  | 2025-11-11 13:52
STK-040 |  | PRJ-005 | Document preparation- sridevi agencies | modify the delivarable document to present to RK. Giving ad and explaining the process | Gokul | 2025-11-01 | 2025-11-02 | COMPLETED | 100 |  | 2025-11-11 13:52
STK-041 |  | PRJ-014 | workflow update- Autoposting | improving the workflow to support posting videos to both instgram and facebook | Gokul | 2025-10-31 | 2025-11-04 | COMPLETED | 100 |  | 2025-11-11 13:52
STK-042 |  | PRJ-014 | service account setup-n8n | update the google credentials to google service account to avoid reconnecting often | Gokul | 2025-11-02 | 2025-11-04 | COMPLETED | 100 |  | 2025-11-11 13:52
STK-043 |  | PRJ-014 | naming workflow-n8n | ad tags and proper names to all the current workflows so that it is easy to identify and access | Gokul | 2025-10-31 | 2025-11-02 | COMPLETED | 100 |  | 2025-11-11 13:52
STK-044 |  | PRJ-013 | admin- office keys | make 2 copies of office keys to give to sumanth and naveen | Gokul |  |  | NOT_STARTED
STK-045 |  | PRJ-012 | collect statments-financial | collect statments from ravi sir and fill it in exepenses sheet | Gokul |  |  | NOT_STARTED
STK-046 |  | PRJ-003 | collect feedback form-INR | Ask charan again to fill the feedback form and store the response in drive | Gokul |  |  | COMPLETED | 100 |  | 2025-11-11 13:52
STK-047 |  | PRJ-008 | sheet preparation-video list | prepare the sheet for making videos for CC demo to team ...assign tasks accordingly | Gokul | 2025-11-01 | 2025-11-01 | ON_HOLD |  |  | 2025-11-11 13:52
STK-048 | TK-003 | PRJ-001 | deployment using ansible | Need to deploy the fully functional code of geopulse 1.0 using ansible | Sumanth | 2025-11-03 | 2025-11-07 | COMPLETED | 100 | the ansible package itself is not supporting widows so that... we used windows subsystem linux(WSL) to run the ansible.. | 2025-10-11 09:42
STK-049 | TK-003 | PRJ-001 | sentinel hub image retrieve | using notebooks in google colabs to run the code in the sentinel hub documentations and seeing the result.. | Sumanth | 2025-11-03 | 2025-11-07 | COMPLETED | 100 | still unable to retrieve the images even using the same code may be need subscription.. | 2025-07-11 10:25 | sumanth
STK-050 |  | PRJ - 001 | GeoPulse Deployment | GeoPulse Deployment through with docker and ansible. | Vishnu |  |  | IN_PROGRESS
STK-051 |  | PRJ-007 | Content - creation to post plan | create a detailed plan and flow for daily content posting which uses minimum time and gives maximum information to the viewers | Gokul | 2025-11-10 |  | IN_PROGRESS |  |  | 2025-11-11 13:51
STK-052 |  | PRJ-019 | workflow- clockify summary, autoposting update . | change the LLM to summarize and give crisp combined summary to CEO update the autoposting workflow to support all formats video to instagram | Gokul | 2025-11-08 | 2025-11-08 | COMPLETED | 100 |  | 2025-11-11 13:53
STK-053 |  |  | `lead gen- finding pattern | finding the pattern to search for projects and freelance works Globally and locally | Gokul | 2025-11-10 | 2025-11-11 | COMPLETED | 100 |  | 2025-11-11 13:50
STK-054 |  |  | delivery- first cry | shedule meeting with jithendra and explain the workflow . | Gokul | 2025-11-11 | 2025-11-11 | IN_PROGRESS |  |  | 2025-11-11 10:36
STK-055 |  |  | reqruitment for DL | schedule meet with team and brainstorm ideas fo DL requirtment | Gokul | 2025-11-11 | 2025-11-11 | COMPLETED | 100 |  | 2025-11-11 13:53
STK-056 |  |  | ad creation for sridevi agencies | complete the ad for sridevi agencies and deliver to RK. | Gokul | 2025-11-09 | 2025-11-10 | COMPLETED | 100 |  | 2025-11-11 13:53
STK-057 |  | PRJ - 001 | GeoPulse Deployment | GeoPulse Deployment through with docker and ansible. | Vishnu
STK-058 | TK-028 | PRJ-016 | Fixiing dropdown and ids- PTA | In project tracking sheet the dropdowns and ids have to be user friendly that means have to keep easy to access | Sathwik | 2025-11-03 | 2025-11-05 | IN_PROGRESS | 75 |  | 2025-11-11 13:05
STK-059 | TK-026 | PRJ-001 | Threshold List sharing | lisiting the thresholds clearly detailed ly | Sathwik | 2025-10-28 | 2025-11-13 | IN_PROGRESS | 50 |  | 2025-11-11 14:03
STK-060 | TK-030 | PRJ-001 | automations for DL | complete and update all the workflows in n8n make it useful to DL tasks | Gokul | 2025-11-06 | 2025-12-05 | COMPLETED | 100 |  | 2025-11-11 13:57
STK-061 |  | PRJ-014 | update- n8n | update n8n to latest version to support all nodes | Gokul | 2025-11-07 | 2025-11-10 | COMPLETED | 100 |  | 2025-11-11 13:54 | datalegos@gmail.com
STK-062 |  | PRJ-021 | Updating chat bot.. | the website chatbot need to get updated | Sumanth | 2025-11-12 | 2025-11-12 | COMPLETED | 100 | The chatbot updated and reviewed by raki and pushed the code to the git "https://github.com/datalegos/our_kraft/tree/main/sumanth/chatbot" | 13/11/25 09:55
STK-063 |  | PRJ-021 | Updating the dl website. | cci-chat (internshp page is updated with proper responsive). | Vishnu | 2025-11-10 | 2025-11-10 | COMPLETED | 100 |  | 2025-11-11 14:08
STK-064 |  | PRJ-021 | geopulse 2.0 input updates | there are 4 types of the inputs can use be able to upload.. | Sumanth | 2025-11-10 | 2025-11-11 | COMPLETED | 100 | completed the task and used the externel api to get the coordinates based on the street address which is "https://my.locationiq.com/dashboard/?firstLogin=1#accesstoken" there are 4 types of the inputs can use be able to upload.. and pushed to git "https://github.com/datalegos/GeoPulse/tree/geopulse-2.0/Geo_Pulse" | 13/11/25 09:53
STK-065 |  | PRJ-006 | Neo4j | Learning udemy neo4j course | Sumanth | 2025-11-11 | 2025-11-15 | COMPLETED | 100 | completed the course of the neo4j in udemy "https://www.udemy.com/share/103rQq3@GDd4KIlRNt6-GVwVEM4J6BoPS9_WZWKKI5u6EmpqPstez5mr_hcndqq47ekei8q1XQ==/" | 19/11/25 09:55
STK-066 | TK-033 | PRJ-020 | Creating Synthetic Data-PEV | Creating Synthetic Data of Patients and Insurance Providers | Sathwik | 2025-11-08 | 2025-11-09 | COMPLETED | 100 |  | 2025-11-11 14:38
STK-067 | TK-033 | PRJ-020 | Analyzing of workflow-PEV | Analyzing how many workflows and how they work | Sathwik | 2025-11-08 | 2025-11-09 | COMPLETED | 100 |  | 2025-11-11 14:38
STK-068 | TK-033 | PRJ-020 | Creating UiPath Workflows-PEV | Creating all steps of workflows and run under Main xaml | Sathwik | 2025-11-08 | 2025-11-11 | COMPLETED | 100 |  | 2025-11-11 14:51
STK-069 | TK-033 | PRJ-020 | Demo on PEV | Have to give UiPath PEV automation to Ravi Sir | Sathwik | 2025-11-11 | 2025-11-11 | COMPLETED | 100 |  | 2025-11-11 14:53
STK-070 |  |  | Learning - UI | Completed UI/UX - design thinking course | Vishnu | 2025-09-11 | 2025-11-11 | Pending |  |  | 2025-12-11 11:27
STK-071 |  |  | Modifying DL Website | modify the images in the home page, aboutus page, contact pages.. | Vishnu |  |  | Pending |  |  | 2025-11-11 17:36
STK-072 |  |  | lead generation | demo of project searching tasks sheet for ravi sir | Gokul | 2025-11-12 | 2025-11-12 | Pending |  |  | 2025-12-11 09:55
STK-073 |  | PRJ-006 | payment gateway | the payment gateway need to be do and getting aware on the technology | Sumanth | 2025-11-09 | 2025-11-09 | COMPLETED | 100 | The payment gateway was implemented as poc and pushed to git.. "https://github.com/datalegos/our_kraft/tree/main/sumanth/payment_gateway" | 13/11/25 09:51
STK-074 | [7 empty] | Pending |  |  | 13/11/25 09:45
STK-075 |  |  | Send 10-15 personalized connection requests. | LinkedIn | Gokul | 2025-11-13 | 2025-11-13 | COMPLETED |  |  | 14/11/25 10:23
STK-076 |  |  | Engage on 10 posts from experts. | LinkedIn | Gokul | 2025-11-13 | 2025-11-13 | COMPLETED |  |  | 14/11/25 10:23
STK-077 |  |  | Send value-driven DMs to warm leads. | LinkedIn | Gokul | 2025-11-13 | 2025-11-13 | CANCELLED |  |  | 14/11/25 10:23
STK-078 |  |  | Post short graph insights or visuals. | LinkedIn | Gokul | 2025-11-12 | 2025-11-12 | CANCELLED |  |  | 14/11/25 10:24
STK-079 |  |  | Post 3 insights with #Neo4j #GraphData. | Twitter/X | Gokul | 2025-11-12 | 2025-11-12 | CANCELLED |  |  | 14/11/25 10:24
STK-080 |  |  | Engage with 5 influencer tweets. | Twitter/X | Gokul | 2025-11-13 | 2025-11-13 | COMPLETED |  |  | 14/11/25 10:24
STK-081 |  |  | Share a project or case study on Reddit. | Neo4j Forum/Reddit/Discord | Gokul | 2025-11-12 | 2025-11-12 | ON_HOLD |  |  | 14/11/25 10:24
STK-082 |  |  | Create short Neo4j explainer video. | YouTube | Gokul | 2025-11-12 | 2025-11-12 | CANCELLED |  |  | 14/11/25 10:24
STK-083 |  |  | Post about 'Free 15-min Graph Strategy Audit'. | LinkedIn | Gokul | 2025-11-12 | 2025-11-12 | CANCELLED |  |  | 14/11/25 10:24
STK-084 | TK-026 | PRJ-001 | Reconstructing and Gathering of thresholds with ChatGPT | By mentioning clear and detailed info of GeoPulse tool and prompting more better to get the finest results of thresholds | Sathwik | 2025-11-13 | 2025-11-17 | IN_PROGRESS | 75 |  | 19/11/25 09:55
STK-085 | TK-026 | PRJ-001 | Geopulse Construction threshold testing | Threshold testing on 4 different construction including demolished once | Sathwik | 2025-11-13 | 2025-11-19 | IN_PROGRESS | 50 |  | 19/11/25 09:55
STK-086 | TK-026 | PRJ-001 | Geopulse Agriculture land threshold testing | Threshold testing on 4 different agriculture lands | Sathwik | 2025-11-13 | 2025-11-19 | IN_PROGRESS | 50 |  | 14/11/25 02:17
STK-087 | TK-026 | PRJ-001 | Geopulse mining area threshold testing | Threshold testing on 4 different mining areas | Sathwik | 2025-11-13 | 2025-11-19 | IN_PROGRESS | 25 |  | 19/11/25 09:55
STK-088 | TK-026 | PRJ-001 | Geopulse water bodies threshold testing | Threshold testing on 4 different water bodies | Sathwik | 2025-11-13 | 2025-11-19 | NOT_STARTED | 0 |  | 19/11/25 09:55
STK-089 |  | PRJ-001 | Geopulse Theme implementation | Modifying neew themes in Geopulse Apllication | Vishnu | 2025-11-13 | 2025-11-13 | IN_PROGRESS |  |  | 13/11/25 11:05
STK-090 |  | PRJ-021 | Modifying DL Website. | Implementig new chat bot in DL website | Vishnu | 2025-11-13 |  | IN_PROGRESS |  |  | 14/11/25 16:44
STK-091 | TK-033 | PRJ-020 | Demo video on Patient Eligibility verification | Prepare ppt and also has to capture the execution and add them together and prepare the demo video | Sathwik | 2025-11-13 | 2025-11-15 | COMPLETED | 100 | Finished the Demo vedio and uploaded in drive shared the drive link to Ravi Sir | 15/11/25 19:20
STK-092 | TK-032 | PRJ-021 | Send 10-15 personalized connection requests. | LinkedIn | Gokul | 2025-11-14 | 2025-11-14 | COMPLETED |  |  | 18/11/25 09:49
STK-093 | TK-032 | PRJ-021 | Engage on 10 posts from experts. | LinkedIn | Gokul | 2025-11-14 | 2025-11-14 | COMPLETED |  |  | 18/11/25 09:49
STK-094 | TK-032 | PRJ-021 | Send value-driven DMs to warm leads. | LinkedIn | Gokul | 2025-11-14 | 2025-11-14 | COMPLETED |  |  | 18/11/25 09:49
STK-095 | TK-032 | PRJ-021 | Post short graph insights or visuals. | LinkedIn | Gokul | 2025-11-14 | 2025-11-14 | COMPLETED |  |  | 18/11/25 09:49
STK-096 | TK-032 | PRJ-021 | Post 3 insights with #Neo4j #GraphData. | Twitter/X | Gokul | 2025-11-14 | 2025-11-14 | CANCELLED |  |  | 18/11/25 09:50
STK-097 | TK-032 | PRJ-021 | Engage with 5 influencer tweets. | Twitter/X | Gokul | 2025-11-14 | 2025-11-14 | COMPLETED |  |  | 18/11/25 09:49
STK-098 | TK-032 | PRJ-021 | Share a project or case study on Reddit. | Neo4j Forum/Reddit/Discord | Gokul | 2025-11-14 | 2025-11-14 | CANCELLED |  |  | 18/11/25 09:49
STK-099 | TK-032 | PRJ-021 | Create short Neo4j explainer video. | YouTube | Gokul | 2025-11-14 | 2025-11-14 | ON_HOLD |  |  | 18/11/25 09:50
STK-100 | TK-030 | PRJ-001 | Post about 'Free 15-min Graph Strategy Audit'. | LinkedIn | Gokul | 2025-11-14 | 2025-11-14 | CANCELLED |  |  | 18/11/25 09:50
STK-101 | TK-31 |  | Learning Neo4j | Started Training Neo4j | Vishnu | 2025-11-14 | 16/11/2025 | COMPLETED | 100 |  | 21/11/25 11:39
STK-102 |  |  | Send 10-15 personalized connection requests. | LinkedIn | Gokul | 2025-11-16 06:02 | 2025-11-14 06:02 | COMPLETED |  |  | 18/11/25 09:50
STK-103 |  |  | Engage on 10 posts from experts. | LinkedIn | Gokul | 2025-11-16 06:02 | 2025-11-14 06:02 | COMPLETED |  |  | 18/11/25 09:50
STK-104 |  |  | Send value-driven DMs to warm leads. | LinkedIn | Gokul | 2025-11-16 06:02 | 2025-11-14 06:02 | COMPLETED |  |  | 17/11/25 09:44
STK-106 |  |  | Engage with 5 influencer tweets. | Twitter/X | Gokul | 2025-11-16 06:03 | 2025-11-14 06:02 | COMPLETED |  |  | 17/11/25 09:45
STK-105 |  |  | Share a project or case study on Reddit. | Neo4j Forum/Reddit/Discord | Gokul | 2025-11-16 06:03 | 2025-11-14 06:02 | COMPLETED |  |  | 17/11/25 09:45
STK-106 |  |  | Create short Neo4j explainer video. | YouTube | Gokul | 2025-11-16 06:03 | 2025-11-14 06:02 | COMPLETED |  |  | 17/11/25 09:45
STK-107 |  |  | Post about 'Free 15-min Graph Strategy Audit'. | LinkedIn | Gokul | 2025-11-16 06:03 | 2025-11-14 06:02 | COMPLETED |  |  | 17/11/25 09:45
STK-108 |  |  | Send 10-15 personalized connection requests. | LinkedIn | Gokul | 2025-11-17 06:02 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-109 |  |  | Engage on 10 posts from experts. | LinkedIn | Gokul | 2025-11-17 06:02 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-110 |  |  | Send value-driven DMs to warm leads. | LinkedIn | Gokul | 2025-11-17 06:02 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-111 |  |  | Post short graph insights or visuals. | LinkedIn | Gokul | 2025-11-17 06:02 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-112 |  |  | Follow up with accepted connections. | LinkedIn | Gokul | 2025-11-17 06:02 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-113 |  |  | Write long-form post or article. | LinkedIn | Gokul | 2025-11-17 06:03 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-114 |  |  | Add GitHub/YouTube links to posts. | LinkedIn | Gokul | 2025-11-17 06:03 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-115 |  |  | Follow up with warm leads via email. | LinkedIn | Gokul | 2025-11-17 06:03 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-116 |  |  | Publish article on Neo4j + AI business case. | Medium/Hashnode | Gokul | 2025-11-17 06:03 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-117 |  |  | Repurpose LinkedIn content to Medium articles. | Medium/Hashnode | Gokul | 2025-11-17 06:03 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-118 |  |  | Comment on trending Medium posts in Neo4j. | Medium/Hashnode | Gokul | 2025-11-17 06:03 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-119 |  |  | Post 3 insights with #Neo4j #GraphData. | Twitter/X | Gokul | 2025-11-17 06:03 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-120 |  |  | Engage with 5 influencer tweets. | Twitter/X | Gokul | 2025-11-17 06:03 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-121 |  |  | Tag Neo4j community members in posts. | Twitter/X | Gokul | 2025-11-17 06:03 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-122 |  |  | Share links to Medium/LinkedIn posts. | Twitter/X | Gokul | 2025-11-17 06:03 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-123 |  |  | Answer 2-3 questions on Neo4j Forum. | Neo4j Forum/Reddit/Discord | Gokul | 2025-11-17 06:03 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-124 |  |  | Share a project or case study on Reddit. | Neo4j Forum/Reddit/Discord | Gokul | 2025-11-17 06:03 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-125 |  |  | Create short Neo4j explainer video. | YouTube | Gokul | 2025-11-17 06:03 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-126 |  |  | Extract 20 potential leads (CTOs/VPs). | Apollo.io | Gokul | 2025-11-17 06:03 | 2025-11-17 06:02 | COMPLETED |  |  | 17/11/25 12:47
STK-127 |  |  | Send 3 Upwork proposals for Neo4j gigs. | Upwork | Gokul | 2025-11-17 06:03 | 2025-11-17 06:02 | CANCELLED |  |  | 18/11/25 09:19
STK-128 |  |  | Post about 'Free 15-min Graph Strategy Audit'. | LinkedIn | Gokul | 2025-11-17 06:03 | 2025-11-17 06:02 | IN_PROGRESS |  |  | 18/11/25 09:19
STK-129 |  |  | Review metrics and update dashboard. | Dashboard | Gokul | 2025-11-17 06:03 | 2025-11-17 06:02 | COMPLETED |  |  | 18/11/25 09:19
STK-130 |  |  | Send 10-15 personalized connection requests. | LinkedIn | Gokul | 2025-11-18 06:02 | 2025-11-18 06:02 | IN_PROGRESS |  |  | 18/11/25 09:39
STK-131 |  |  | Engage on 10 posts from experts. | LinkedIn | Gokul | 2025-11-18 06:02 | 2025-11-18 06:02 | IN_PROGRESS |  |  | 18/11/25 09:40
STK-132 |  |  | Send value-driven DMs to warm leads. | LinkedIn | Gokul | 2025-11-18 06:03 | 2025-11-18 06:02 | IN_PROGRESS |  |  | 18/11/25 09:40
STK-133 |  |  | Engage with 5 influencer tweets. | Twitter/X | Gokul | 2025-11-18 06:03 | 2025-11-18 06:02 | IN_PROGRESS |  |  | 18/11/25 09:40
STK-134 |  |  | Share a project or case study on Reddit. | Neo4j Forum/Reddit/Discord | Gokul | 2025-11-18 06:03 | 2025-11-18 06:02 | IN_PROGRESS |  |  | 18/11/25 09:40
STK-135 |  |  | Create short Neo4j explainer video. | YouTube | Gokul | 2025-11-18 06:03 | 2025-11-18 06:02 | IN_PROGRESS |  |  | 18/11/25 09:40
STK-136 |  |  | Post about 'Free 15-min Graph Strategy Audit'. | LinkedIn | Gokul | 2025-11-18 06:03 | 2025-11-18 06:02 | IN_PROGRESS |  |  | 18/11/25 09:40
STK-137 |  | PRJ-006 | Neo4j | Learning udemy neo4j course | Sumanth | 2025-11-19 | 2025-11-19 | COMPLETED | 100 | completed the course of the knowledge graphs as RAGS.... "https://www.udemy.com/course/knowledge-graphs-rag/" | 21/11/25 11:30
STK-138 |  | PRJ-24 | agentic flow | implementing agentic flow for a business case | Sumanth | 2025-11-21 | 2025-11-25 | COMPLETED | 0 |  | 21/11/25 11:29
STK-139 |  | PRJ-006 | neo4j data modelling | Learning udemy neo4j data modelling course | Sumanth | 2025-11-21 | 2025-11-21 | COMPLETED | 100 | completing course of data modelling in neo4j academy site.. "https://www.udemy.com/course/knowledge-graphs-rag/" | 21/11/25 11:32
STK-140 |  | PRJ-24 | data modelling for business usecase | using the dataset and creating neo4j scema based on the businesscase | Sumanth | 2025-11-21 | 2025-11-25 | COMPLETED | 0 |  | 21/11/25 11:36
|  |  | Neo4j Certification Exam | Completed exam and Certificate posted in linkedin. | Vishnu | 20/11/2025 | 20/11/2025 | COMPLETED | 100 |  | 21/11/25 11:47

## Subtasks_History (hidden)
subtask_id | task_id | project_id | subtask_name | description | assigned to | start_date | due_date | status | completion_percentage | comments | last_updated | updated_by
STK-001 |  | PRJ-003 | delivarables document template preparation | preapare the delivarbales document template and 1. collect all the deliverbales and give it to INR | Gokul | 2025-10-23 | 2025-10-27 | COMPLETED | 100 |  | 2025-12-11 09:55
STK-002 |  | PRJ-003 | feed back form template preparation | preapare the feedback form document template and 1. validate with team and collect feed abck from INR | Gokul | 2025-10-23 | 2025-10-27 | COMPLETED | 100 |  | 2025-12-11 09:55
STK-003 |  | PRJ-004 | modifying 3 day digital marketing template | team discussion and modifying 3 day digital marketing template to execute for first cry take only whats necesary and assign tasks to collect the necessary requirments and divide among team | Gokul | 2025-10-17 | 2025-10-24 | COMPLETED | 100 | discussed and finazlised the template and arranged the folders in google drive | 15/11/25 19:14
STK-004 |  | PRJ-004 | autoposting workflow for firstcry | complete the workflow for autoposting , validate ,demo and deliver it to client | Gokul | 2025-10-23 | 2025-10-28 | COMPLETED | 100 | need to get validation mail from meta | 2025-12-11 09:56
STK-005 |  | PRJ-008 | learning video preparation | validate the topics written till now on one note and check whats needed prepare a template and assaign the video making to ravi sir. | Gokul | 2025-10-22 | 2025-10-27 | IN_PROGRESS | 75 | sent to team sumanth added few topics and most of the topics a re covered. Oct 28: keep all topics in one sheet. gokul and ravi discuss later to prioratize.
STK-006 |  | PRJ-011 | expense filling | check the sheet, see from which months entry is missing and collect pending statments from ravi sir and fill the sheet | Gokul | 2025-10-22 | 2025-11-03 | NOT_STARTED |  | oct 28: will review. | 15/11/25 19:15
STK-007 |  | PRJ-012 | daily standups and meet for team | conduct daily standups for team to track progress and updates. | Gokul | 2025-10-27 |  | IN_PROGRESS |  |  | 2025-12-11 09:56
STK-008 |  | PRJ-012 | tasks and clockify filling | enetring the taks and sheets for daily followups and tracking, filling the clockify regularly | Gokul | 2025-10-27 |  | IN_PROGRESS
STK-009 |  | PRJ-013 | veo3 video creation (Subcription utilizaion) | we have multiple subscriptions for veo3. this limit will expire at the end of the date. we should maintain a list to utilize the subsceription very well by scheduleing and maintaiing the backlog. check the tasks and if needed any videos genrate it and if not needed use some theme and craft the propt and check results | Gokul | 2025-10-27 |  | IN_PROGRESS |  | veo 3 video making in progress | 2025-12-11 09:57
STK-010 |  | PRJ-007 | template preparation for content posting | prepare a template to make the daily content posting fast and efficient | Gokul | 2025-10-24 | 2025-10-28 | IN_PROGRESS |  |  | 2025-12-11 09:57
STK-011 |  | PRJ-001 | modifying organization page | Removed delete button from Organization Setup admin page | Vishnu | 2025-10-24 | 2025-10-24 | COMPLETED | 100
STK-012 |  | PRJ-001 | modifying reports page | Removed debug information section from Reports page | Vishnu | 2025-10-24 | 2025-10-24 | COMPLETED | 100
STK-013 |  | PRJ-001 | modifying profile section | Fixed contact phone field fetching in user profile | Vishnu | 2025-10-24 | 2025-10-24 | COMPLETED | 100
STK-014 |  | PRJ-001 | modifying surveyor dashboard page. | Diagnosed authentication issues with surveyor dashboard | Vishnu | 2025-10-24 | 2025-10-24 | COMPLETED | 100
STK-015 |  | PRJ-003 | clear delivarables document template preparation | preapare the delivarbales document template and 1. collect all the deliverbales and give it to INR | Naveen | 2025-10-23 | 2025-10-27 | IN_PROGRESS | 75
STK-016 |  | PRJ-008 | learning video preparation | Verifying all the topics written till now on one note and check whats needed prepare a template and keep it in onenote [DL_techteam, common, ccstudentapproach, training topics for cc raki] | Naveen | 2025-10-22 | 2025-10-27 | IN_PROGRESS | 75
STK-017 |  | PRJ-013 | veo3 video creation | check the tasks and if needed any videos generate it and if not needed use some local images videos and do it both AI and Manual | Naveen | 2025-10-27 |  | NOT_STARTED
STK-018 |  | PRJ-012 | daily tasks and enter into the clockify filling | note down the daily tasks must enter into the clockify and sheets and followup and tracking and fillup regularly. | Naveen | 2025-10-27 |  | IN_PROGRESS
STK-019 |  | PRJ-004 | modifying 3 day digital marketing template | team discussion on 3 day digital marketing template and updated new ideas | Naveen | 2025-10-17 | 2025-10-24 | COMPLETED | 100
STK-020 |  | PRJ-004 | modifying 3 day digital marketing template | team discussion on 3 day digital marketing template and updated new ideas | Sathwik | 2025-10-17 | 2025-10-24 | COMPLETED | 100
STK-021 | TK-010 | PRJ-001 | Testing admin access and remaining functionalities | Testing every section in the admin login to ensure all functionalities work clear and attached the report link at the comments | Sathwik | 2025-09-22 | 2025-09-29 | COMPLETED | 100 | Testing Report
STK-022 | TK-011 | PRJ-001 | Testing surveyor access and remaining functionalities | Testing every section in the surveyor login to ensure all functionalities work clear and attached the report link at the comments | Sathwik | 2025-09-22 | 2025-09-29 | COMPLETED | 100 | Testing Report
STK-023 | TK-026 | PRJ-001 | Testing bi threshold | testing the bi threshold with different formulas to make sure get the best accuracy | Sathwik | 2025-10-24 | 2025-10-28 | COMPLETED | 100
STK-024 | TK-026 | PRJ-001 | Testing vi threshold | testing the vi threshold with different formulas to make sure get the best accuracy | Sathwik | 2025-10-25 | 2025-10-28 | COMPLETED | 100
STK-025 | TK-026 | PRJ-001 | Testing mixed area of construction and vegitation | testing the both bi and vi threshold with different formulas to make sure get the best accuracy that gets the both construction and vegitation change in changed pixels | Sathwik | 2025-10-27 | 2025-10-28 | IN_PROGRESS | 50
STK-026 | TK-027 | PRJ-016 | creating sheet for the project tracking | create the spreadsheet with the orgainsed tabs and columns that helps to identify and can automate with easy detection of the columns under their specific tabs | Sathwik | 2025-09-08 | 2025-09-15 | COMPLETED | 100 | Project Tracking Automation
STK-027 | TK-028 | PRJ-016 | Creating automation on the project tracker | create the automation on project tracking that identify the updations in subtasks and remaining on status and completion percentage | Sathwik | 2025-09-15 | 2025-10-31 | IN_PROGRESS | 75 | https://workflow.data-legos.com/workflow/85SRf8oGE6E6cARW Needs to add the Discord bot
STK-028 | TK-028 | PRJ-016 | Create automation on due date and deadline notifier | this automation checks the due date and deadline and notifiy according to the date | Sathwik | 2025-09-22 | 2025-10-31 | IN_PROGRESS | 75 | https://workflow.data-legos.com/workflow/85SRf8oGE6E6cARW Needs to add the Discord bot
STK-029 |  | PRJ-001 | Analysing Imagery.. | analyzing the possibilities using the cursor.. | Sumanth | 2025-10-27 | 2025-06-11 | COMPLETED | 100 | analysis completed and pushed the analysis files to the git in datalegos geopulse analysis branch | 15/11/25 19:05
STK-030 |  | PRJ-001 | Debugging Hardcoding Values |  | Vishnu | 2025-10-27 | 2025-10-27 | COMPLETED | 100 |  | 2025-12-11 00:36
STK-031 | TK-003 | PRJ-002 | "geopulse" Doing analysis on imagery requirement | The feature enables the users to get the the visually understandable changes from the two dates given for geopulse 2.0 the detailed analysis synopsis : ----> finding the api which is best for our usecase to get more clear image as well as cost effective.. ----> checking possibility to whether can we use the google earth/any other api by replacing sentinel hub to get the band values.. | Sumanth | 2025-10-28 | 2025-10-28 | COMPLETED | 100 | the analysis on the different apis are done and used them and looked their webpages in order to aware on those apis how to use them for our purose. | 2025-12-11 00:36
STK-032 | TK-003 | PRJ-002 | "geopulse" Developing pocs on imagery requirement using different APIs | Developing the pocs for geopulse 2.0 to get images.. tasks: ----> Implimenting the demo codes for the api to retrieve images.. pushed the code to git "https://github.com/datalegos/GeoPulse/tree/analysis/image_retrieval_analysis" | Sumanth | 2025-10-28 | 2025-10-29 | COMPLETED | 100 | the POC and demo video and md documentation analysis are developed and pushed to git. | 15/11/25 19:06
STK-033 |  | PRJ-001 | Fixing the bugs and errors. | Fixing the bugs and errors in the GP-1.0 | Vishnu | 2025-10-28 | 2025-10-28 | COMPLETED | 100 |  | 2025-12-11 00:36
STK-034 |  | PRJ-001 |  | Rearranging the shared_folder structure and testing the application | Vishnu | 2025-10-29 | 2025-10-29 | COMPLETED | 100
STK-035 |  | PRJ-001 | Moving application to Deployment | Moved applicatoin sucessfully to the production server. | Vishnu | 2025-10-30 | 2025-10-29 | COMPLETED | 100
STK-036 |  | PRJ-004 | Document prepartion-first cry | modify the delivarable document to present to first cry explaining the usage and scope of autoposting workflow | Gokul | 2025-10-31 | 2025-11-02 | COMPLETED | 100 |  | 2025-11-11 13:52
STK-037 |  | PRJ-004 | meeting setup- first cry | setting meeting at the convinince time and delivering the handover documents | Gokul | 2025-10-31 | 2025-11-02 | COMPLETED | 100 | meeting set for monday | 2025-11-11 13:52
STK-038 |  | PRJ-005 | followup-sridevi agencies | follow up with RK anna about GBS status and check for any update or modifications | Gokul | 2025-11-01 | 2025-11-02 | COMPLETED | 100 | mobile num not woking- check and update the num | 2025-11-11 13:52
STK-039 |  | PRJ-005 | ad creation-sridevi agencies | Generate AI ads for sridevi agencies ..shoot the store video ...mix with song and create a complete 1 min ad video | Gokul | 2025-11-01 | 2025-11-03 | COMPLETED | 100 |  | 2025-11-11 13:52
STK-040 |  | PRJ-005 | Document preparation- sridevi agencies | modify the delivarable document to present to RK. Giving ad and explaining the process | Gokul | 2025-11-01 | 2025-11-02 | COMPLETED | 100 |  | 2025-11-11 13:52
STK-041 |  | PRJ-014 | workflow update- Autoposting | improving the workflow to support posting videos to both instgram and facebook | Gokul | 2025-10-31 | 2025-11-04 | COMPLETED | 100 |  | 2025-11-11 13:52
STK-042 |  | PRJ-014 | service account setup-n8n | update the google credentials to google service account to avoid reconnecting often | Gokul | 2025-11-02 | 2025-11-04 | COMPLETED | 100 |  | 2025-11-11 13:52
STK-043 |  | PRJ-014 | naming workflow-n8n | ad tags and proper names to all the current workflows so that it is easy to identify and access | Gokul | 2025-10-31 | 2025-11-02 | COMPLETED | 100 |  | 2025-11-11 13:52
STK-044 |  | PRJ-013 | admin- office keys | make 2 copies of office keys to give to sumanth and naveen | Gokul |  |  | NOT_STARTED
STK-045 |  | PRJ-012 | collect statments-financial | collect statments from ravi sir and fill it in exepenses sheet | Gokul |  |  | NOT_STARTED
STK-046 |  | PRJ-003 | collect feedback form-INR | Ask charan again to fill the feedback form and store the response in drive | Gokul |  |  | COMPLETED | 100 |  | 2025-11-11 13:52
STK-047 |  | PRJ-008 | sheet preparation-video list | prepare the sheet for making videos for CC demo to team ...assign tasks accordingly | Gokul | 2025-11-01 | 2025-11-01 | ON_HOLD |  |  | 2025-11-11 13:52
STK-048 | TK-003 | PRJ-001 | deployment using ansible | Need to deploy the fully functional code of geopulse 1.0 using ansible | Sumanth | 2025-11-03 | 2025-11-07 | COMPLETED | 100 | the ansible package itself is not supporting widows so that... we used windows subsystem linux(WSL) to run the ansible.. | 2025-10-11 09:42
STK-049 | TK-003 | PRJ-001 | sentinel hub image retrieve | using notebooks in google colabs to run the code in the sentinel hub documentations and seeing the result.. | Sumanth | 2025-11-03 | 2025-11-07 | COMPLETED | 100 | still unable to retrieve the images even using the same code may be need subscription.. | 2025-07-11 10:25 | sumanth
STK-050 |  | PRJ - 001 | GeoPulse Deployment | GeoPulse Deployment through with docker and ansible. | Vishnu |  |  | IN_PROGRESS
STK-051 |  | PRJ-007 | Content - creation to post plan | create a detailed plan and flow for daily content posting which uses minimum time and gives maximum information to the viewers | Gokul | 2025-11-10 |  | IN_PROGRESS |  |  | 2025-11-11 13:51
STK-052 |  | PRJ-019 | workflow- clockify summary, autoposting update . | change the LLM to summarize and give crisp combined summary to CEO update the autoposting workflow to support all formats video to instagram | Gokul | 2025-11-08 | 2025-11-08 | COMPLETED | 100 |  | 2025-11-11 13:53
STK-053 |  |  | `lead gen- finding pattern | finding the pattern to search for projects and freelance works Globally and locally | Gokul | 2025-11-10 | 2025-11-11 | COMPLETED | 100 |  | 2025-11-11 13:50
STK-054 |  |  | delivery- first cry | shedule meeting with jithendra and explain the workflow . | Gokul | 2025-11-11 | 2025-11-11 | IN_PROGRESS |  |  | 2025-11-11 10:36
STK-055 |  |  | reqruitment for DL | schedule meet with team and brainstorm ideas fo DL requirtment | Gokul | 2025-11-11 | 2025-11-11 | COMPLETED | 100 |  | 2025-11-11 13:53
STK-056 |  |  | ad creation for sridevi agencies | complete the ad for sridevi agencies and deliver to RK. | Gokul | 2025-11-09 | 2025-11-10 | COMPLETED | 100 |  | 2025-11-11 13:53
STK-057 |  | PRJ - 001 | GeoPulse Deployment | GeoPulse Deployment through with docker and ansible. | Vishnu
STK-058 | TK-028 | PRJ-016 | Fixiing dropdown and ids- PTA | In project tracking sheet the dropdowns and ids have to be user friendly that means have to keep easy to access | Sathwik | 2025-11-03 | 2025-11-05 | IN_PROGRESS | 75 |  | 2025-11-11 13:05
STK-059 | TK-026 | PRJ-001 | Threshold List sharing | lisiting the thresholds clearly detailed ly | Sathwik | 2025-10-28 | 2025-11-13 | IN_PROGRESS | 50 |  | 2025-11-11 14:03
STK-060 | TK-030 | PRJ-001 | automations for DL | complete and update all the workflows in n8n make it useful to DL tasks | Gokul | 2025-11-06 | 2025-12-05 | COMPLETED | 100 |  | 2025-11-11 13:57
STK-061 |  | PRJ-014 | update- n8n | update n8n to latest version to support all nodes | Gokul | 2025-11-07 | 2025-11-10 | COMPLETED | 100 |  | 2025-11-11 13:54 | datalegos@gmail.com
STK-062 |  | PRJ-021 | Updating chat bot.. | the website chatbot need to get updated | Sumanth | 2025-11-12 | 2025-11-12 | COMPLETED | 100 | The chatbot updated and reviewed by raki and pushed the code to the git "https://github.com/datalegos/our_kraft/tree/main/sumanth/chatbot" | 13/11/25 09:55
STK-063 |  | PRJ-021 | Updating the dl website. | cci-chat (internshp page is updated with proper responsive). | Vishnu | 2025-11-10 | 2025-11-10 | COMPLETED | 100 |  | 2025-11-11 14:08
STK-064 |  | PRJ-021 | geopulse 2.0 input updates | there are 4 types of the inputs can use be able to upload.. | Sumanth | 2025-11-10 | 2025-11-11 | COMPLETED | 100 | completed the task and used the externel api to get the coordinates based on the street address which is "https://my.locationiq.com/dashboard/?firstLogin=1#accesstoken" there are 4 types of the inputs can use be able to upload.. and pushed to git "https://github.com/datalegos/GeoPulse/tree/geopulse-2.0/Geo_Pulse" | 13/11/25 09:53
STK-065 |  | PRJ-006 | Neo4j | Learning udemy neo4j course | Sumanth | 19/11/2025 | 19/11/2025 | IN_PROGRESS | 0 |  | 19/11/25 09:58
STK-066 | TK-033 | PRJ-020 | Creating Synthetic Data-PEV | Creating Synthetic Data of Patients and Insurance Providers | Sathwik | 2025-11-08 | 2025-11-09 | COMPLETED | 100 |  | 2025-11-11 14:38
STK-067 | TK-033 | PRJ-020 | Analyzing of workflow-PEV | Analyzing how many workflows and how they work | Sathwik | 2025-11-08 | 2025-11-09 | COMPLETED | 100 |  | 2025-11-11 14:38
STK-068 | TK-033 | PRJ-020 | Creating UiPath Workflows-PEV | Creating all steps of workflows and run under Main xaml | Sathwik | 2025-11-08 | 2025-11-11 | COMPLETED | 100 |  | 2025-11-11 14:51
STK-069 | TK-033 | PRJ-020 | Demo on PEV | Have to give UiPath PEV automation to Ravi Sir | Sathwik | 2025-11-11 | 2025-11-11 | COMPLETED | 100 |  | 2025-11-11 14:53
STK-070 |  |  | Learning - UI | Completed UI/UX - design thinking course | Vishnu | 2025-09-11 | 2025-11-11 | Pending |  |  | 2025-12-11 11:27
STK-071 |  |  | Modifying DL Website | modify the images in the home page, aboutus page, contact pages.. | Vishnu |  |  | Pending |  |  | 2025-11-11 17:36
STK-072 |  |  | lead generation | demo of project searching tasks sheet for ravi sir | Gokul | 2025-11-12 | 2025-11-12 | Pending |  |  | 2025-12-11 09:55
STK-073 |  | PRJ-006 | payment gateway | the payment gateway need to be do and getting aware on the technology | Sumanth | 2025-11-09 | 2025-11-09 | COMPLETED | 100 | The payment gateway was implemented as poc and pushed to git.. "https://github.com/datalegos/our_kraft/tree/main/sumanth/payment_gateway" | 13/11/25 09:51
STK-074 | [7 empty] | Pending |  |  | 13/11/25 09:45
STK-075 |  |  | Send 10-15 personalized connection requests. | LinkedIn | Gokul | 2025-11-13 | 2025-11-13 | COMPLETED |  |  | 14/11/25 10:23
STK-076 |  |  | Engage on 10 posts from experts. | LinkedIn | Gokul | 2025-11-13 | 2025-11-13 | COMPLETED |  |  | 14/11/25 10:23
STK-077 |  |  | Send value-driven DMs to warm leads. | LinkedIn | Gokul | 2025-11-13 | 2025-11-13 | CANCELLED |  |  | 14/11/25 10:23
STK-078 |  |  | Post short graph insights or visuals. | LinkedIn | Gokul | 2025-11-12 | 2025-11-12 | CANCELLED |  |  | 14/11/25 10:24
STK-079 |  |  | Post 3 insights with #Neo4j #GraphData. | Twitter/X | Gokul | 2025-11-12 | 2025-11-12 | CANCELLED |  |  | 14/11/25 10:24
STK-080 |  |  | Engage with 5 influencer tweets. | Twitter/X | Gokul | 2025-11-13 | 2025-11-13 | COMPLETED |  |  | 14/11/25 10:24
STK-081 |  |  | Share a project or case study on Reddit. | Neo4j Forum/Reddit/Discord | Gokul | 2025-11-12 | 2025-11-12 | ON_HOLD |  |  | 14/11/25 10:24
STK-082 |  |  | Create short Neo4j explainer video. | YouTube | Gokul | 2025-11-12 | 2025-11-12 | CANCELLED |  |  | 14/11/25 10:24
STK-083 |  |  | Post about 'Free 15-min Graph Strategy Audit'. | LinkedIn | Gokul | 2025-11-12 | 2025-11-12 | CANCELLED |  |  | 14/11/25 10:24
STK-084 | TK-026 | PRJ-001 | Reconstructing and Gathering of thresholds with ChatGPT | By mentioning clear and detailed info of GeoPulse tool and prompting more better to get the finest results of thresholds | Sathwik | 13/11/2025 | 17/11/2025 | IN_PROGRESS | 75 |  | 19/11/25 09:55
STK-085 | TK-026 | PRJ-001 | Geopulse Construction threshold testing | Threshold testing on 4 different construction including demolished once | Sathwik | 13/11/2025 | 19/11/2025 | IN_PROGRESS | 50 |  | 19/11/25 09:55
STK-086 | TK-026 | PRJ-001 | Geopulse Agriculture land threshold testing | Threshold testing on 4 different agriculture lands | Sathwik | 2025-11-13 | 2025-11-16 | IN_PROGRESS | 50 |  | 14/11/25 02:17
STK-087 | TK-026 | PRJ-001 | Geopulse mining area threshold testing | Threshold testing on 4 different mining areas | Sathwik | 13/11/2025 | 19/11/2025 | IN_PROGRESS | 25 |  | 19/11/25 09:55
STK-088 | TK-026 | PRJ-001 | Geopulse water bodies threshold testing | Threshold testing on 4 different water bodies | Sathwik | 13/11/2025 | 19/11/2025 | NOT_STARTED | 0 |  | 19/11/25 09:55
STK-089 |  | PRJ-001 | Geopulse Theme implementation | Modifying neew themes in Geopulse Apllication | Vishnu | 2025-11-13 | 2025-11-13 | IN_PROGRESS |  |  | 13/11/25 11:05
STK-090 |  | PRJ-021 | Modifying DL Website. | Implementig new chat bot in DL website | Vishnu | 2025-11-13 |  | IN_PROGRESS |  |  | 14/11/25 16:44
STK-091 | TK-033 | PRJ-020 | Demo video on Patient Eligibility verification | Prepare ppt and also has to capture the execution and add them together and prepare the demo video | Sathwik | 13/11/2025 | 15/11/2025 | COMPLETED | 100 | Finished the Demo vedio and uploaded in drive shared the drive link to Ravi Sir | 15/11/25 19:20
STK-092 | TK-032 | PRJ-021 | Send 10-15 personalized connection requests. | LinkedIn | Gokul | 14/11/2025 | 14/11/2025 | IN_PROGRESS |  |  | 18/11/25 09:49
STK-093 | TK-032 | PRJ-021 | Engage on 10 posts from experts. | LinkedIn | Gokul | 14/11/2025 | 14/11/2025 | IN_PROGRESS |  |  | 18/11/25 09:49
STK-094 | TK-032 | PRJ-021 | Send value-driven DMs to warm leads. | LinkedIn | Gokul | 14/11/2025 | 14/11/2025 | IN_PROGRESS |  |  | 18/11/25 09:49
STK-095 | TK-032 | PRJ-021 | Post short graph insights or visuals. | LinkedIn | Gokul | 14/11/2025 | 14/11/2025 | IN_PROGRESS |  |  | 18/11/25 09:49
STK-096 | TK-032 | PRJ-021 | Post 3 insights with #Neo4j #GraphData. | Twitter/X | Gokul | 14/11/2025 | 14/11/2025 | IN_PROGRESS |  |  | 18/11/25 09:50
STK-097 | TK-032 | PRJ-021 | Engage with 5 influencer tweets. | Twitter/X | Gokul | 14/11/2025 | 14/11/2025 | IN_PROGRESS |  |  | 18/11/25 09:49
STK-098 | TK-032 | PRJ-021 | Share a project or case study on Reddit. | Neo4j Forum/Reddit/Discord | Gokul | 14/11/2025 | 14/11/2025 | IN_PROGRESS |  |  | 18/11/25 09:49
STK-099 | TK-032 | PRJ-021 | Create short Neo4j explainer video. | YouTube | Gokul | 14/11/2025 | 14/11/2025 | IN_PROGRESS |  |  | 18/11/25 09:50
STK-100 | TK-030 | PRJ-001 | Post about 'Free 15-min Graph Strategy Audit'. | LinkedIn | Gokul | 14/11/2025 | 14/11/2025 | IN_PROGRESS |  |  | 18/11/25 09:50
STK-101 | TK-31 |  | Learning Neo4j | Started Training Neo4j | Vishnu | 2025-11-14 | 16/11/2025 | IN_PROGRESS |  |  | 14/11/25 17:01
STK-102 |  |  | Send 10-15 personalized connection requests. | LinkedIn | Gokul | 16/11/2025 | 14/11/2025 | NOT_STARTED | 0 |  | 18/11/25 09:50
STK-103 |  |  | Engage on 10 posts from experts. | LinkedIn | Gokul | 16/11/2025 | 14/11/2025 | NOT_STARTED | 0 |  | 18/11/25 09:50
STK-104 |  |  | Send value-driven DMs to warm leads. | LinkedIn | Gokul | 16/11/2025 | 14/11/2025 | NOT_STARTED | 0 |  | 17/11/25 09:44
STK-105 |  |  | Share a project or case study on Reddit. | Neo4j Forum/Reddit/Discord | Gokul | 16/11/2025 | 14/11/2025 | NOT_STARTED | 0 |  | 17/11/25 09:45
STK-106 |  |  | Create short Neo4j explainer video. | YouTube | Gokul | 16/11/2025 | 14/11/2025 | NOT_STARTED | 0 |  | 17/11/25 09:45
STK-107 |  |  | Post about 'Free 15-min Graph Strategy Audit'. | LinkedIn | Gokul | 16/11/2025 | 14/11/2025 | NOT_STARTED | 0 |  | 17/11/25 09:45
STK-108 |  |  | Send 10-15 personalized connection requests. | LinkedIn | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-109 |  |  | Engage on 10 posts from experts. | LinkedIn | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-110 |  |  | Send value-driven DMs to warm leads. | LinkedIn | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-111 |  |  | Post short graph insights or visuals. | LinkedIn | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-112 |  |  | Follow up with accepted connections. | LinkedIn | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-113 |  |  | Write long-form post or article. | LinkedIn | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-114 |  |  | Add GitHub/YouTube links to posts. | LinkedIn | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-115 |  |  | Follow up with warm leads via email. | LinkedIn | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-116 |  |  | Publish article on Neo4j + AI business case. | Medium/Hashnode | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-117 |  |  | Repurpose LinkedIn content to Medium articles. | Medium/Hashnode | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-118 |  |  | Comment on trending Medium posts in Neo4j. | Medium/Hashnode | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-119 |  |  | Post 3 insights with #Neo4j #GraphData. | Twitter/X | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-120 |  |  | Engage with 5 influencer tweets. | Twitter/X | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-121 |  |  | Tag Neo4j community members in posts. | Twitter/X | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-122 |  |  | Share links to Medium/LinkedIn posts. | Twitter/X | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-123 |  |  | Answer 2-3 questions on Neo4j Forum. | Neo4j Forum/Reddit/Discord | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-124 |  |  | Share a project or case study on Reddit. | Neo4j Forum/Reddit/Discord | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-125 |  |  | Create short Neo4j explainer video. | YouTube | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-126 |  |  | Extract 20 potential leads (CTOs/VPs). | Apollo.io | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 17/11/25 12:47
STK-127 |  |  | Send 3 Upwork proposals for Neo4j gigs. | Upwork | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 18/11/25 09:19
STK-128 |  |  | Post about 'Free 15-min Graph Strategy Audit'. | LinkedIn | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 18/11/25 09:19
STK-129 |  |  | Review metrics and update dashboard. | Dashboard | Gokul | 17/11/2025 | 17/11/2025 | NOT_STARTED | 0 |  | 18/11/25 09:19
STK-130 |  |  | Send 10-15 personalized connection requests. | LinkedIn | Gokul | 18/11/2025 | 18/11/2025 | NOT_STARTED | 0 |  | 18/11/25 09:39
STK-131 |  |  | Engage on 10 posts from experts. | LinkedIn | Gokul | 18/11/2025 | 18/11/2025 | NOT_STARTED | 0 |  | 18/11/25 09:40
STK-132 |  |  | Send value-driven DMs to warm leads. | LinkedIn | Gokul | 18/11/2025 | 18/11/2025 | NOT_STARTED | 0 |  | 18/11/25 09:40
STK-133 |  |  | Engage with 5 influencer tweets. | Twitter/X | Gokul | 18/11/2025 | 18/11/2025 | NOT_STARTED | 0 |  | 18/11/25 09:40
STK-134 |  |  | Share a project or case study on Reddit. | Neo4j Forum/Reddit/Discord | Gokul | 18/11/2025 | 18/11/2025 | NOT_STARTED | 0 |  | 18/11/25 09:40
STK-135 |  |  | Create short Neo4j explainer video. | YouTube | Gokul | 18/11/2025 | 18/11/2025 | NOT_STARTED | 0 |  | 18/11/25 09:40
STK-136 |  |  | Post about 'Free 15-min Graph Strategy Audit'. | LinkedIn | Gokul | 18/11/2025 | 18/11/2025 | NOT_STARTED | 0 |  | 18/11/25 09:40
STK-137 |  | PRJ-006 | Neo4j | Learning udemy neo4j course | Sumanth | 19/11/2025 | 19/11/2025 | NOT_STARTED | 0 |  | 19/11/25 11:46

## Instructions
Action | User Does | Script Does
Add new item | Enter name only | Generates ID, date, dropdowns
Select parent | Choose from dropdown | Auto-fills parent project
Edit Subtask | Change fields, select your name | Updates History & timestamps
Complete Subtask | Set % to 100 | Auto-marks as COMPLETED
Use Subtasks_History | Don’t edit manually | Updates automatically

## Team Members (hidden)
assigned to | employee_email
Gokul | gokul.k.raj1436@gmail.com
Sumanth | sgadepalli21@gmail.com
Vishnu | mohanvishnu937@gmail.com
Naveen | gunapaneninaveenkumar@gmail.com
Sathwik | sathwiks222@gmail.com
RaviKiran | ravikiran.ponduri@gmail.com